CorridorIQ

MVP plan and use cases

ML-driven cross-border payment routing, delivered in six MVPs

| Project | PaymentCorridor |
| --- | --- |
| Document | Delivery plan: MVPs and use cases |
| Version | 1.0, draft for discussion |
| Date | 17 October 2026 |

Contents

Summary	3

Roadmap at a glance	4

Actors and external systems	5

MVP 1: Route advisor	6

MVP 2: Calibrated with history	11

MVP 3: Controlled release	14

MVP 4: ML ranking	19

MVP 5: Breadth	22

MVP 6: White-label SaaS	25

Principles and open decisions	28

Appendix: module reference	29

# Summary

CorridorIQ recommends the best corridor for each cross-border payment, explains the choice, and lets a person certify and release it. This plan delivers it in six MVPs that together carry 47 use cases.

Each MVP ships something a bank can use, adds the use cases listed under it, and ends at a gate with measurable exit criteria. MVP 1 recommends routes without touching money movement. The LightGBM model arrives in MVP 4, once real outcome data and checker overrides exist to train it.

## How to read this document

- Roadmap at a glance shows the sequence, gates and indicative durations.

- Actors and external systems defines who and what the use cases refer to.

- One chapter per MVP sets out the goal, scope, boundaries and exit criteria, followed by its use cases.

- Each use case lists the primary actor, trigger, main flow, acceptance criteria and the modules it depends on. Module codes (M1 to M15) are defined in the appendix.

Durations are indicative elapsed time for planning and sequencing only.

# Roadmap at a glance

The six MVPs run in sequence, each ending at a gate. MVP 2's actual outcomes and MVP 3's checker overrides are the training data the MVP 4 model needs, which is why machine learning comes fourth.

| MVP | Goal | Use cases | Duration | Gate |
| --- | --- | --- | --- | --- |
| MVP 1 Route advisor | Prove the recommendations are right without touching money movement. | 10 | 10–12 weeks | Ops agree with top route in ≥80% of cases |
| MVP 2 Calibrated with history | Replace the assumed processing times with what actually happened. | 7 | 6–8 weeks | Time estimates within agreed error band |
| MVP 3 Controlled release | A payment goes from request to release inside CorridorIQ, under full control. | 10 | 12–14 weeks | InfoSec, Compliance and audit sign-off |
| MVP 4 ML ranking | The LightGBM model beats the heuristic ranker. | 7 | 8–10 weeks | Beats heuristic on NDCG@3 in shadow |
| MVP 5 Breadth | Cover more of the bank's volume, client types and routes. | 7 | 8–10 weeks | Agreed share of volume covered |
| MVP 6 White-label SaaS | Serve several banks from one platform, each under its own brand and policies. | 6 | 10–12 weeks | Second bank live by configuration alone |

# Actors and external systems

These are the people and systems the use cases refer to. The last column shows the MVP in which each actor first takes part.

## Actors

| Actor | Role in CorridorIQ | First MVP |
| --- | --- | --- |
| Payments operator (maker) | Captures client requests, reviews ranked corridors, prepares payments for certification. | MVP 1 |
| Bank administrator | Maintains reference data, holiday calendars, rules and users. | MVP 1 |
| Operations analyst | Reviews corridor performance, annotates incidents, monitors estimate accuracy. | MVP 2 |
| Data engineer | Loads historical payment and tracker data, runs data-quality checks. | MVP 2 |
| Treasury operations | Reviews FX timing; acts as second checker for large payments. | MVP 2 |
| Checker | Verifies checks and route, certifies and releases payments, records overrides. | MVP 3 |
| L2 Compliance officer | Reviews screening alerts and records the decision with evidence. | MVP 3 |
| Internal audit or examiner | Reviews the decision record and evidence for any payment. | MVP 3 |
| Data scientist or model owner | Trains, evaluates, promotes and monitors the ranking and estimate models. | MVP 4 |
| Model risk team | Independently validates models before they go live. | MVP 4 |
| Financial institution client | Submits payments on behalf of corporate clients, including by API. | MVP 5 |
| CorridorIQ platform operations | Onboards banks, runs the multi-tenant service, maintains assurance evidence. | MVP 6 |

## External systems

| System | What CorridorIQ uses it for |
| --- | --- |
| Bank payment hub | Receives certified pacs.008 or MT103 messages and sends them to the network. |
| Sanctions screening system | The bank's existing screening service, called for every party and bank on the route. |
| SWIFT gpi Tracker | Supplies status updates for released payments by UETR. |
| FX rate feed | Supplies mid rates and live quotes. |
| Holiday calendar feed and BIC directory | Supply market and bank holidays, and bank identifiers. |

# MVP 1: Route advisor

Goal: Prove the recommendations are right without touching money movement.

## Scope and exit criteria

| Scope | - Reference data (M2), banking calendar (M3), FX and pricing with static daily rates (M4) - Request intake as a structured form (M5) - Route simulation engine (M6), rules and eligibility (M7), transparent weighted ranking v1 (M8) - Operator console route view without the approval panel (M15) |
| --- | --- |
| Boundaries | One design-partner bank, two corridors (USD→JPY and USD→INR), retail and business clients. Reference data comes from the bank's SSI spreadsheet. Operators still key the payment into the bank's existing system. |
| Not in this MVP | Payment release, screening, natural-language intake, the ML model, the financial institution client type, non-bank routes. |
| Exit criteria | - During a 4-week parallel run, operators agree with the top-ranked route in at least 80% of payments. - Every calendar-driven delay in the run period was predicted. |
| Indicative duration | 10–12 weeks |

## Use cases

10 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-1.1 | Capture a payment requirement | Payments operator |
| UC-1.2 | Get ranked corridors for a payment | Payments operator |
| UC-1.3 | Understand why a route was excluded | Payments operator |
| UC-1.4 | Check the banking calendar around the value date | Payments operator |
| UC-1.5 | Inspect a route hop by hop | Payments operator |
| UC-1.6 | Compare cost against time to credit | Payments operator |
| UC-1.7 | Set correspondent preferences | Payments operator |
| UC-1.8 | Maintain reference data | Bank administrator |
| UC-1.9 | Maintain holiday calendars | Bank administrator |
| UC-1.10 | Record the route actually used | Payments operator |

### UC-1.1  Capture a payment requirement

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A client asks to send a cross-border payment. |
| Main flow | - Operator opens a new request and selects the client type (retail or business). - Operator enters destination, amount in USD, charge code (OUR, SHA or BEN), value date, optional arrive-by date, beneficiary name and purpose code. - Operator sets the cost-versus-speed priority. - System validates the inputs and saves the request as a draft. |
| Acceptance criteria | - A value date before the next US business day is rejected with a clear message. - An arrive-by date earlier than the value date is rejected. - Charge code and purpose code are mandatory. - A draft can be reopened and edited until routes are requested. |
| Modules | M5, M3, M15 |

### UC-1.2  Get ranked corridors for a payment

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator selects Find best corridors. |
| Main flow | - System builds every candidate route for the corridor from the correspondent network. - System simulates each hop with local cut-offs, weekends, holidays and processing times to estimate time to credit. - System calculates fees per hop, FX margin and the amount the beneficiary receives under the chosen charge code. - Rules remove ineligible routes; the remaining routes are scored using the priority weighting and ranked. - System shows the recommended route with headline figures, a one-line reason, and the ranked list. |
| Acceptance criteria | - Each eligible route shows time to credit, all-in cost, rate offered and score. - The recommended route is the highest-scoring eligible route. - Changing the priority re-ranks routes without re-entering the request. - Routes that miss the arrive-by date are flagged and ranked lower. - The reason line compares the top route with the cheapest and fastest eligible routes. |
| Modules | M6, M7, M8 v1, M4, M15 |

### UC-1.3  Understand why a route was excluded

| Primary actor | Payments operator |
| --- | --- |
| Trigger | The ranked list contains excluded routes. |
| Main flow | - System lists excluded routes below the eligible ones. - Each excluded route shows the rule or rules that removed it. - Where a calendar rule removed a cheaper route, the summary shows the saving and the later credit date. |
| Acceptance criteria | - Every excluded route shows at least one reason in plain language (cap exceeded, client not eligible, bank excluded, correspondent closed near the value date). - Reasons match the active rule configuration. - The operator can switch off the calendar rule for a request and see the route return with a warning. |
| Modules | M7, M15 |

### UC-1.4  Check the banking calendar around the value date

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator reviews the calendar panel. |
| Main flow | - System shows a 14-day grid from the day before the value date, one row per country on the candidate routes. - Weekends, holidays, the value date and the selected route's credit date are marked. - Hovering a day shows why it is a non-business day. |
| Acceptance criteria | - Friday–Saturday weekends in Bahrain and Saudi Arabia are shown correctly. - India's 2nd and 4th Saturday bank holidays are shown correctly. - US Fedwire and destination holidays match the loaded calendar. |
| Modules | M3, M15 |

### UC-1.5  Inspect a route hop by hop

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator selects a route in the list or on the chart. |
| Main flow | - System shows each bank on the route with BIC, role, local in and out times and any hold (cut-off, holiday, batch window). - System shows the rail between hops (Fedwire, SWIFT, local clearing). - System shows the cost and FX breakdown: principal, fees, FX margin, rate offered, amount converted and amount received. |
| Acceptance criteria | - Times are shown in each bank's local time zone, with the zone label. - Hop fees add up to the fee total shown in the ranked list. - Amount received reflects the OUR, SHA or BEN charge code correctly. |
| Modules | M6, M4, M15 |

### UC-1.6  Compare cost against time to credit

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator reviews the trade-off chart. |
| Main flow | - System plots every route by time to credit and all-in cost. - System draws the best trade-off line across eligible routes. - Operator clicks a point to open that route's detail. |
| Acceptance criteria | - Excluded routes appear but are visually distinct and cannot be selected. - The recommended route is highlighted. |
| Modules | M8 v1, M15 |

### UC-1.7  Set correspondent preferences

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator wants to avoid or favour a correspondent for this request. |
| Main flow | - Operator unticks a bank to exclude it, or stars it as a preferred relationship. - Operator switches the rule that avoids correspondents closed near the value date on or off. - System re-runs the ranking. |
| Acceptance criteria | - Routes through an excluded bank move to the excluded list with the reason that the operator excluded that bank. - A preferred bank adds a small, visible boost to the score; it never overrides a rule. |
| Modules | M7, M8 v1, M15 |

### UC-1.8  Maintain reference data

| Primary actor | Bank administrator |
| --- | --- |
| Trigger | A correspondent, fee, cut-off, cap or route template changes. |
| Main flow | - Administrator imports the SSI spreadsheet or edits records in the admin screen. - Administrator sets an effective date for each change. - System checks BIC formats, missing fields and broken route links, then publishes the new version. |
| Acceptance criteria | - Changes apply from their effective date; earlier requests keep the version they used. - Every change records who made it and when. - A route template that refers to a missing bank cannot be published. |
| Modules | M2 |

### UC-1.9  Maintain holiday calendars

| Primary actor | Bank administrator |
| --- | --- |
| Trigger | A calendar feed update or an unscheduled closure. |
| Main flow | - System loads the holiday feed for every country and bank on the network. - Administrator adds an ad hoc closure for a specific bank or market. - System recalculates estimates for open requests that are affected. |
| Acceptance criteria | - Feed freshness is visible, and a stale feed raises an alert. - Ad hoc closures take precedence over the feed and are logged. |
| Modules | M3 |

### UC-1.10  Record the route actually used

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator has sent the payment through the bank's existing system during the parallel run. |
| Main flow | - Operator records which route was used and, if it differs from the recommendation, why. - System stores the recommendation and the actual choice together. - The product team reviews agreement weekly. |
| Acceptance criteria | - Agreement is reported by corridor and by week. - The report measures the MVP 1 exit criterion of at least 80% agreement. |
| Modules | M15 |

# MVP 2: Calibrated with history

Goal: Replace the assumed processing times with what actually happened.

## Scope and exit criteria

| Scope | - Outcomes warehouse (M13) loaded with 12–24 months of the bank's MT103/pacs.008 and gpi tracker exports - History view, similar-cases panel and incident annotation in the console (M15) - P50 and P90 times from real distributions for each hop, used by the simulation engine (M6) |
| --- | --- |
| Boundaries | Same bank and corridors as MVP 1. Data arrives as periodic exports; live tracker feeds come in MVP 3. |
| Not in this MVP | Payment release, live tracking, the ML model. |
| Exit criteria | - Predicted versus actual time to credit is within an agreed error band, for example a median error under 4 hours on corridors under 72 hours. |
| Indicative duration | 6–8 weeks |

## Use cases

7 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-2.1 | Import historical payments | Data engineer |
| UC-2.2 | Calibrate time estimates from outcomes | System (scheduled) |
| UC-2.3 | Review route performance for a corridor | Operations analyst |
| UC-2.4 | See similar past cases for a new request | Payments operator |
| UC-2.5 | Annotate an incident | Operations analyst |
| UC-2.6 | Review FX history and volatility | Treasury operations |
| UC-2.7 | Monitor estimate accuracy | Operations analyst |

### UC-2.1  Import historical payments

| Primary actor | Data engineer |
| --- | --- |
| Trigger | The design-partner bank provides an export of past payments. |
| Main flow | - Data engineer loads MT103/pacs.008 records and gpi tracker events. - System links records by UETR, maps each payment to its route and hops, and works out actual time to credit and cost. - System produces a data-quality report: unmatched records, missing timestamps and duplicates. |
| Acceptance criteria | - Re-running an import does not create duplicates. - Records that cannot be mapped to a known route are reported, not silently dropped. - Personal data is handled under the bank's data-sharing agreement and masked where it is not needed. |
| Modules | M13 |

### UC-2.2  Calibrate time estimates from outcomes

| Primary actor | System (scheduled) |
| --- | --- |
| Trigger | New outcome data has been loaded. |
| Main flow | - System calculates processing-time distributions per bank, hop and time-of-day band. - The simulation uses these distributions in place of fixed processing times. - Ranked routes show P50 and P90 time to credit. |
| Acceptance criteria | - Hops with enough history use measured values; hops without enough history fall back to defaults and are flagged. - Each calibration run is versioned, so any estimate can be traced to the data behind it. |
| Modules | M13, M6 |

### UC-2.3  Review route performance for a corridor

| Primary actor | Operations analyst |
| --- | --- |
| Trigger | Analyst opens the history view. |
| Main flow | - Analyst selects a corridor. - System shows, for each route: number of cases, median and P90 time to credit, average cost in basis points and straight-through rate. - Analyst opens the underlying list of cases. |
| Acceptance criteria | - Figures reconcile with the case list. - Analyst can filter by date range, client type and amount band. |
| Modules | M13, M15 |

### UC-2.4  See similar past cases for a new request

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator views ranked corridors for a request. |
| Main flow | - System finds past payments on the same corridor with a similar amount, client type and release weekday. - System shows how long each took, what it cost, its outcome and any ops note. - System compares the median time on the recommended route with the current estimate. |
| Acceptance criteria | - Up to six matches are shown, with cases on the recommended route highlighted. - Annotated incidents rank above unannotated cases of similar fit. |
| Modules | M13, M15 |

### UC-2.5  Annotate an incident

| Primary actor | Operations analyst |
| --- | --- |
| Trigger | A payment was delayed, repaired or returned. |
| Main flow | - Analyst opens the case and records the cause (holiday, weekend, missed cut-off, information request, wrong purpose code, other) with a short note. - System adds the annotation to the case and to the corridor's incident list. - The product team reviews new causes for rule or calendar changes. |
| Acceptance criteria | - Causes come from a controlled list, with free text for detail. - Annotated cases are available as labelled data for the MVP 4 model. |
| Modules | M13, M15 |

### UC-2.6  Review FX history and volatility

| Primary actor | Treasury operations |
| --- | --- |
| Trigger | Treasury reviews conversion timing for a currency. |
| Main flow | - System shows 90 days of USD rates for the selected currency and its annualised volatility. - Currencies pegged to the dollar are labelled as pegged. |
| Acceptance criteria | - Chart and volatility figure match the stored rate series. |
| Modules | M4, M15 |

### UC-2.7  Monitor estimate accuracy

| Primary actor | Operations analyst |
| --- | --- |
| Trigger | Weekly review. |
| Main flow | - System compares predicted with actual time to credit for completed payments. - System reports the error by corridor and route, and lists the largest misses. |
| Acceptance criteria | - The report measures the MVP 2 exit criterion. - Each large miss links to its case for annotation. |
| Modules | M13 |

# MVP 3: Controlled release

Goal: A payment goes from request to release inside CorridorIQ, under full control.

## Scope and exit criteria

| Scope | - Identity and access with bank SSO, roles and four-eyes enforcement (M1) - Compliance checks (M9), certification workflow (M10), audit and evidence (M11) - Message building, hand-off to the payment hub and gpi tracking (M12) - Approval panel and tracker in the console (M15) |
| --- | --- |
| Boundaries | Same bank as MVP 1. Ranking stays on the heuristic until MVP 4. Integration with the bank's payment hub takes the longest, so that conversation starts during MVP 1. |
| Not in this MVP | The ML model, natural-language intake, multi-bank tenancy. |
| Exit criteria | - The bank's InfoSec and Compliance teams sign off. - Pilot volume is released with zero control breaches. - Internal audit accepts the audit pack. |
| Indicative duration | 12–14 weeks |

## Use cases

10 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-3.1 | Sign in and act within a role | All bank users |
| UC-3.2 | Run pre-release compliance checks | System, reviewed by the checker |
| UC-3.3 | Give a retail client the pre-payment disclosure | Payments operator |
| UC-3.4 | Certify and release a payment | Checker |
| UC-3.5 | Override the recommended route | Checker |
| UC-3.6 | Approve a payment above $1 million | Checker and second checker (Treasury Operations) |
| UC-3.7 | Resolve a screening alert | L2 Compliance officer |
| UC-3.8 | Return a payment to the client, or reject it | Checker |
| UC-3.9 | Track a released payment | Payments operator, client service |
| UC-3.10 | Review the audit trail for a payment | Internal audit or examiner |

### UC-3.1  Sign in and act within a role

| Primary actor | All bank users |
| --- | --- |
| Trigger | A user opens CorridorIQ. |
| Main flow | - User signs in through the bank's single sign-on. - System loads the user's role: maker, checker, L2 compliance, treasury or administrator. - Screens and actions are limited to that role. |
| Acceptance criteria | - A maker cannot certify a payment they prepared. - Role changes are logged and take effect at the next sign-in. - Sessions time out after the bank's configured idle period. |
| Modules | M1 |

### UC-3.2  Run pre-release compliance checks

| Primary actor | System, reviewed by the checker |
| --- | --- |
| Trigger | A route is selected for certification. |
| Main flow | - System sends every party and every bank on the route to the bank's sanctions screening system. - System checks Travel Rule data for transfers of $3,000 or more. - System validates the ISO 20022 structured postal address for debtor and creditor. - System validates the purpose code and checks counterparty limits and nostro funding. - Results appear as checklist items, each with a status. |
| Acceptance criteria | - A possible sanctions match blocks release until L2 Compliance clears it. - A missing structured address field, such as town name, is marked incomplete and blocks release, in line with CBPR+ rules from November 2026. - Each check records the list or rule version it used. |
| Modules | M9 |

### UC-3.3  Give a retail client the pre-payment disclosure

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A consumer remittance is ready for certification. |
| Main flow | - System generates the disclosure: fees, exchange rate, amount received and date available. - Operator gives it to the client and records the acknowledgement. - System supports a cancellation request within the cancellation period. |
| Acceptance criteria | - Disclosure figures match the selected route exactly. - The disclosure is stored with the payment record. - A cancellation within the period stops a payment not yet released, or starts a recall. |
| Modules | M9, M11 |

### UC-3.4  Certify and release a payment

| Primary actor | Checker |
| --- | --- |
| Trigger | Every checklist item is complete. |
| Main flow | - Checker reviews route, amount, beneficiary and expected credit date. - Checker confirms each checklist item and selects Certify and release. - System builds the pacs.008 (or MT103 where needed), validates it against CBPR+ rules and assigns a UETR. - System hands the message to the bank's payment hub and records the acknowledgement. |
| Acceptance criteria | - Release is possible only when every item is confirmed. - The message the hub receives matches the certified route and amounts. - A hub rejection returns the payment to the checker's queue with the reason. |
| Modules | M10, M12 |

### UC-3.5  Override the recommended route

| Primary actor | Checker |
| --- | --- |
| Trigger | The checker prefers a lower-ranked route. |
| Main flow | - Checker selects another eligible route. - System marks it as an override and asks for a written reason. - Checker certifies as normal. |
| Acceptance criteria | - A reason of at least 12 characters is required. - The override, its reason and the route's rank are logged and become training labels for MVP 4. - Excluded routes cannot be selected. |
| Modules | M10, M11 |

### UC-3.6  Approve a payment above $1 million

| Primary actor | Checker and second checker (Treasury Operations) |
| --- | --- |
| Trigger | The amount is above the dual-control threshold. |
| Main flow | - The first checker certifies. - System routes the payment to the treasury queue. - The second checker confirms amount, route and value date, then releases. |
| Acceptance criteria | - The second checker is a different person from the maker and the first checker. - The bank can configure the threshold. |
| Modules | M10, M1 |

### UC-3.7  Resolve a screening alert

| Primary actor | L2 Compliance officer |
| --- | --- |
| Trigger | Screening returns a possible match. |
| Main flow | - System holds the payment and places it in the L2 queue with the match details. - Officer reviews identity documents and evidence. - Officer clears it as a false positive with evidence, or confirms the match and blocks the payment. |
| Acceptance criteria | - Release stays blocked until the officer records a decision. - Evidence and decision are attached to the case. - A non-bank route never carries a payment with an open alert. |
| Modules | M9, M10 |

### UC-3.8  Return a payment to the client, or reject it

| Primary actor | Checker |
| --- | --- |
| Trigger | Data is missing, or the payment should not go ahead. |
| Main flow | - Checker selects Return to client with the missing items, or Reject with a reason. - System notifies the operator and keeps the case open (return) or closes it (reject). |
| Acceptance criteria | - A rejected payment is never debited. - A returned payment keeps its history when resubmitted. |
| Modules | M10 |

### UC-3.9  Track a released payment

| Primary actor | Payments operator, client service |
| --- | --- |
| Trigger | A payment has been released. |
| Main flow | - System receives gpi tracker updates for the UETR. - System shows each hop's status, such as ACSP and ACCC, with timestamps. - System alerts the operator when a payment passes its P90 estimate without being credited. |
| Acceptance criteria | - Status updates appear as the tracker reports them. - Actual time and cost flow into the outcomes warehouse automatically. |
| Modules | M12, M13 |

### UC-3.10  Review the audit trail for a payment

| Primary actor | Internal audit or examiner |
| --- | --- |
| Trigger | An audit sample or a regulatory request. |
| Main flow | - Auditor searches by UETR, date, client or checker. - System shows the full record: request inputs, routes evaluated, rule and engine versions, rates, checks, approvals, overrides and timestamps. - Auditor exports the record as an evidence pack. |
| Acceptance criteria | - Records cannot be edited or deleted. - The export reproduces exactly what the checker saw at certification. |
| Modules | M11 |

# MVP 4: ML ranking

Goal: The LightGBM model beats the heuristic ranker.

## Scope and exit criteria

| Scope | - Scoring and ranking v2: LightGBM ranker plus time and cost regressors, with SHAP explanations (M8) - MLOps and model governance: feature store, retraining, registry, shadow runs, monitoring (M14) - Model and governance view, and score explanations in route detail (M15) |
| --- | --- |
| Boundaries | Runs in shadow first and becomes the main ranker only after validation. Training labels come from MVP 2 (actual outcomes) and MVP 3 (checker overrides); building the model earlier would mean training it on synthetic data. |
| Not in this MVP | New corridors and client types (MVP 5). |
| Exit criteria | - In shadow, NDCG@3 beats the heuristic by an agreed margin. - Independent model validation is complete. - The checker override rate falls. |
| Indicative duration | 8–10 weeks |

## Use cases

7 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-4.1 | Train the ranking and estimate models | Data scientist |
| UC-4.2 | Run a candidate model in shadow | Data scientist |
| UC-4.3 | Promote or roll back a model | Model owner, model risk team |
| UC-4.4 | Explain a recommendation | Payments operator, checker |
| UC-4.5 | Learn from checker overrides | System |
| UC-4.6 | Monitor model health | Model owner |
| UC-4.7 | Publish the model card and governance view | Model owner, auditor |

### UC-4.1  Train the ranking and estimate models

| Primary actor | Data scientist |
| --- | --- |
| Trigger | The weekly schedule, or a manual run. |
| Main flow | - Pipeline builds features from outcomes, incidents, calendars, FX and overrides. - Pipeline trains the LightGBM ranker (LambdaRank objective) and the time and cost regressors. - Pipeline evaluates on a holdout period and registers the candidate with its metrics. |
| Acceptance criteria | - Training can be reproduced from the registered data snapshot and code version. - Holdout metrics include NDCG@3, time-to-credit error and cost error. |
| Modules | M14, M8 |

### UC-4.2  Run a candidate model in shadow

| Primary actor | Data scientist |
| --- | --- |
| Trigger | A candidate model is registered. |
| Main flow | - System scores live requests with both the current ranker and the candidate. - Operators see only the current ranker's output. - System compares both with the route that actually performed best. |
| Acceptance criteria | - Shadow scoring adds no visible delay for operators. - A comparison report is available by corridor and by week. |
| Modules | M14 |

### UC-4.3  Promote or roll back a model

| Primary actor | Model owner, model risk team |
| --- | --- |
| Trigger | Shadow results meet the promotion criteria. |
| Main flow | - Model owner submits the validation pack. - Model risk team approves or rejects it. - On approval the candidate becomes the live ranker; the previous version stays available. |
| Acceptance criteria | - Promotion requires a recorded approval. - Rollback to the previous model needs no code deployment. |
| Modules | M14 |

### UC-4.4  Explain a recommendation

| Primary actor | Payments operator, checker |
| --- | --- |
| Trigger | A user opens route detail. |
| Main flow | - System shows how much each factor added to or took from the route's score: cost, time to credit, historical straight-through rate, calendar exposure, compliance risk, deadline fit and preferred relationship. - System shows a confidence level based on the lead over the next route. |
| Acceptance criteria | - Contributions are SHAP values from the live model version. - Confidence labels (High, Medium, Close call) follow documented thresholds. |
| Modules | M8, M15 |

### UC-4.5  Learn from checker overrides

| Primary actor | System |
| --- | --- |
| Trigger | The weekly training run. |
| Main flow | - Pipeline collects overrides and their reasons since the last run. - Reasons are grouped and used as labels or features. - The model card reports the override-rate trend. |
| Acceptance criteria | - Repeated overrides for the same pattern change future rankings after retraining. |
| Modules | M14 |

### UC-4.6  Monitor model health

| Primary actor | Model owner |
| --- | --- |
| Trigger | Continuous. |
| Main flow | - System tracks feature drift (PSI), predicted versus actual time to credit, calendar feed freshness and sanctions list version. - System raises an alert when a signal crosses its threshold. |
| Acceptance criteria | - Every signal has a documented threshold and owner. - Alerts reach the model owner and the operations lead. |
| Modules | M14 |

### UC-4.7  Publish the model card and governance view

| Primary actor | Model owner, auditor |
| --- | --- |
| Trigger | A model is promoted. |
| Main flow | - System updates the model card: version, training window, row count, parameters, holdout performance and retraining cadence. - The governance view shows feature importance, monitoring status and the human-in-the-loop policy. |
| Acceptance criteria | - Every live model has a current model card. - Earlier model cards stay accessible. |
| Modules | M14, M15 |

# MVP 5: Breadth

Goal: Cover more of the bank's volume, client types and routes.

## Scope and exit criteria

| Scope | - Natural-language intake with confirmation chips, and a pain.001 API for FI clients (M5) - The financial institution client type, with its fee rules and FX tiers (M4, M7) - UAE, Saudi Arabia and Germany corridors, with Gulf-weekend handling (M2, M3, M6, M7) - Non-bank payout partner and economy batch routes (M2, M6, M7) - Live FX quote lock and preferred-correspondent weighting (M4, M8) |
| --- | --- |
| Boundaries | Natural-language intake can move earlier if sales needs it for demos; it never routes a payment without operator confirmation. |
| Not in this MVP | Onboarding further banks (MVP 6). |
| Exit criteria | - The supported corridors cover an agreed share of the bank's outbound volume. |
| Indicative duration | 8–10 weeks |

## Use cases

7 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-5.1 | Describe a payment in plain language | Payments operator |
| UC-5.2 | Submit payments by API | Financial institution client |
| UC-5.3 | Route a financial institution payment | Payments operator |
| UC-5.4 | Route to the UAE, Saudi Arabia and Germany | Payments operator |
| UC-5.5 | Use the non-bank payout partner | Payments operator |
| UC-5.6 | Choose the economy batch route | Payments operator |
| UC-5.7 | Lock an FX quote | Payments operator, checker |

### UC-5.1  Describe a payment in plain language

| Primary actor | Payments operator |
| --- | --- |
| Trigger | Operator types or pastes the client's request. |
| Main flow | - Operator enters free text, for example: send $10,000 to my son in Japan for school fees, due Wednesday. - System extracts amount, destination, client type, urgency, purpose, value date and deadline. - System shows each value as a chip and fills the form. - Operator confirms or corrects the fields before routing. |
| Acceptance criteria | - Nothing is routed without operator confirmation. - Values the system is unsure of are left blank, not guessed. - Extraction accuracy is measured on a test set of real request wording. |
| Modules | M5 |

### UC-5.2  Submit payments by API

| Primary actor | Financial institution client |
| --- | --- |
| Trigger | The client's system sends a payment instruction. |
| Main flow | - Client sends a pain.001 message to the CorridorIQ API. - System validates it and creates a request. - System returns an acknowledgement and, if configured, the recommended route and quote. |
| Acceptance criteria | - Invalid messages are rejected with ISO 20022 status reasons. - API calls are authenticated and rate-limited per client. |
| Modules | M5 |

### UC-5.3  Route a financial institution payment

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A request is made on behalf of an FI or corporate client. |
| Main flow | - Operator selects the FI client type, or the API sets it. - System applies FI fee rules, large-ticket FX tiers and SHA as the default charge code. - Retail-only and non-bank routes are excluded with reasons. |
| Acceptance criteria | - The large-ticket FX tier applies from the configured amount. - Counterparty limits are checked for the FI. |
| Modules | M7, M4 |

### UC-5.4  Route to the UAE, Saudi Arabia and Germany

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A request to a newly supported corridor. |
| Main flow | - System builds routes through the configured New York, London and Gulf hubs. - The calendar rule handles Gulf weekends, for example a Thursday value date routed through Manama. - Corridors with currencies pegged to the dollar show negligible FX timing risk. |
| Acceptance criteria | - The simulation reproduces known historical incidents on these corridors. |
| Modules | M2, M3, M6, M7 |

### UC-5.5  Use the non-bank payout partner

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A retail payment under the partner's cap. |
| Main flow | - System includes the payout partner as a candidate route. - System applies the per-transfer cap and the retail-only rule. - Payout shows as instant on the local rail. |
| Acceptance criteria | - The route is excluded above the cap, for FI clients, and whenever a screening alert is open. |
| Modules | M2, M7 |

### UC-5.6  Choose the economy batch route

| Primary actor | Payments operator |
| --- | --- |
| Trigger | A small payment where cost matters more than speed. |
| Main flow | - System includes the weekly netting route for amounts under its cap. - The simulation holds the payment until the next batch run. - System checks the expected credit against any arrive-by date. |
| Acceptance criteria | - The estimate reflects the next batch, including when release falls just after a batch cut-off. - The route is flagged when it misses the client's deadline. |
| Modules | M6, M7 |

### UC-5.7  Lock an FX quote

| Primary actor | Payments operator, checker |
| --- | --- |
| Trigger | A route is selected for certification. |
| Main flow | - System requests a live rate for the route's conversion bank and margin tier. - System shows the rate and its expiry time. - If it expires before release, the system requotes and asks the checker to confirm the new figures. |
| Acceptance criteria | - A released payment always carries an unexpired quote. - Disclosure figures are regenerated after a requote. |
| Modules | M4 |

# MVP 6: White-label SaaS

Goal: Serve several banks from one platform, each under its own brand and policies.

## Scope and exit criteria

| Scope | - Full tenant isolation, per-bank branding and policies (M1, M7, M10) - Onboarding tooling and standard import templates (M1, M2) - SOC 2 readiness and usage metering for billing (M1, M11, M15) |
| --- | --- |
| Boundaries | Whether models train per bank or on pooled data from several banks is an open decision; pooling needs each bank's written agreement. |
| Not in this MVP | New product lines outside cross-border routing. |
| Exit criteria | - A second bank is onboarded through configuration alone, with no code changes. |
| Indicative duration | 10–12 weeks |

## Use cases

6 use cases are delivered in this MVP.

| ID | Use case | Primary actor |
| --- | --- | --- |
| UC-6.1 | Onboard a new bank | CorridorIQ platform operations, bank administrator |
| UC-6.2 | Apply the bank's brand | Bank administrator |
| UC-6.3 | Configure bank-specific rules and policies | Bank administrator |
| UC-6.4 | Keep each bank's data separate | Platform operations, bank InfoSec |
| UC-6.5 | Meter usage for billing | Platform operations |
| UC-6.6 | Provide assurance evidence to banks | Platform operations, bank InfoSec |

### UC-6.1  Onboard a new bank

| Primary actor | CorridorIQ platform operations, bank administrator |
| --- | --- |
| Trigger | A new bank signs up. |
| Main flow | - Platform operations creates the tenant and configures single sign-on. - Bank administrator imports reference data, calendars and users with standard templates. - Platform runs configuration checks and enables the bank. |
| Acceptance criteria | - A bank goes live through configuration alone, with no code changes. - An onboarding checklist shows what is complete and what is missing. |
| Modules | M1, M2 |

### UC-6.2  Apply the bank's brand

| Primary actor | Bank administrator |
| --- | --- |
| Trigger | A bank is being set up, or rebrands. |
| Main flow | - Administrator uploads the logo and sets colours and display name. - The console, disclosures and client-facing documents use the bank's brand. |
| Acceptance criteria | - No CorridorIQ branding appears on client-facing documents unless the bank chooses it. |
| Modules | M1, M15 |

### UC-6.3  Configure bank-specific rules and policies

| Primary actor | Bank administrator |
| --- | --- |
| Trigger | A bank sets or changes its policies. |
| Main flow | - Administrator sets caps, the dual-control threshold, preferred correspondents, fee schedules and override policy. - Each change is versioned and needs a second administrator's approval. |
| Acceptance criteria | - One bank's settings never affect another bank. |
| Modules | M1, M7, M10 |

### UC-6.4  Keep each bank's data separate

| Primary actor | Platform operations, bank InfoSec |
| --- | --- |
| Trigger | Continuous. |
| Main flow | - Every request, record and model artefact is tagged to a tenant. - Access controls and encryption keys are separate for each tenant. - Any pooled model training across banks happens only with each bank's written agreement. |
| Acceptance criteria | - Penetration tests confirm no cross-tenant access. - Each bank's data-residency choice is recorded. |
| Modules | M1, M14 |

### UC-6.5  Meter usage for billing

| Primary actor | Platform operations |
| --- | --- |
| Trigger | Month end. |
| Main flow | - System counts requests routed, payments released and API calls per bank. - A monthly usage report feeds invoicing. |
| Acceptance criteria | - Usage reconciles with the audit log. |
| Modules | M11, M15 |

### UC-6.6  Provide assurance evidence to banks

| Primary actor | Platform operations, bank InfoSec |
| --- | --- |
| Trigger | A bank's annual review or a new bank's due diligence. |
| Main flow | - Platform maintains SOC 2 control evidence, access reviews and penetration-test results. - Banks download current reports from an assurance page. |
| Acceptance criteria | - Evidence is current for the audit period. |
| Modules | M1, M11 |

# Principles and open decisions

## Principles that shape the plan

- Sign a design-partner bank before MVP 1. Reference data and payment history come from that bank; without them MVP 2 and MVP 4 stall.

- Integrate rather than build sanctions screening, holiday calendars, the BIC directory and FX rates. Use the providers the bank already has.

- Rules always run before the model, and the deterministic engine stays. The model only ranks routes the engine and rules have already marked feasible; it never overrides a rule. This also makes model validation easier.

- The bank remains the regulated party. CorridorIQ recommends routes and prepares messages; the bank's checker releases through the bank's own payment hub. The bank's counsel should confirm this model.

- CBPR+ structured addresses become mandatory in November 2026. Address validation is therefore a basic requirement for MVP 3, not a nice-to-have.

## Open decisions

These need an owner and a date before or during MVP 1.

- Which design-partner bank, and the data-sharing agreement for its SSI data and payment history.

- The interface to that bank's payment hub (API, file or message queue).

- Whether MVP 1 starts with USD→JPY and USD→INR, or with the partner bank's two highest-volume corridors.

- Holiday calendar and BIC directory providers.

- Per-bank or pooled model training once more than one bank is live.

# Appendix: module reference

Use cases refer to these modules by code. The last column shows the MVP in which each module is first delivered.

| Code | Module | What it does | First delivered |
| --- | --- | --- | --- |
| Foundations |  |  |  |
| M1 | Tenant, identity and access | SSO (SAML/OIDC), roles, four-eyes enforcement, white-label branding, tenant isolation | MVP 3 (basic), MVP 6 (full) |
| M2 | Reference data | Bank and BIC directory, correspondent relationships and SSIs, route templates, fees, cut-offs and caps, versioned by effective date | MVP 1 |
| M3 | Banking calendar | Holidays by country and bank, weekend patterns, Fedwire closures; business-day and cut-off arithmetic as an API | MVP 1 |
| M4 | FX and pricing | Mid-rate feed, margin tiers by amount band, OUR/SHA/BEN charge maths, quote lock with expiry | MVP 1 (static), MVP 5 (live lock) |
| Decisioning |  |  |  |
| M5 | Request intake | Structured form, then a pain.001 API, then natural-language parsing confirmed by the operator | MVP 1 (form), MVP 5 (NL, API) |
| M6 | Route simulation engine | Feasible paths from the correspondent graph; hop-by-hop timing with cut-offs, calendars and batch windows | MVP 1 |
| M7 | Rules and eligibility | Caps, eligibility, exclusions, calendar conflicts, non-bank restrictions, screening blocks; reason codes | MVP 1 |
| M8 | Scoring and ranking | v1 transparent weighted score; v2 LightGBM ranker and regressors with SHAP and confidence | MVP 1 (v1), MVP 4 (v2) |
| Control and compliance |  |  |  |
| M9 | Compliance checks | Sanctions screening connector, Travel Rule, CBPR+ structured address, Reg E disclosures, purpose codes | MVP 3 |
| M10 | Certification workflow | Checklist, dual approval, L2 escalation, overrides with reasons, return and reject, queues | MVP 3 |
| M11 | Audit and evidence | Append-only record per payment: inputs, versions, rates, decision; exportable | MVP 3 |
| Execution and learning |  |  |  |
| M12 | Messaging and tracking | pacs.008/MT103 build and validation, UETR, payment-hub hand-off, gpi tracker status | MVP 3 |
| M13 | Outcomes warehouse | Historical and live payments with actual time and cost; incident annotation | MVP 2 |
| M14 | MLOps and model governance | Feature store, retraining, registry, shadow runs, drift monitoring, model card | MVP 4 |
| M15 | Operator console | Route, history and governance views, plus reporting | Grows with every MVP |